## 00 Overview
MPBCDC Employee Management System — Implementation Tracker
Source: MPBCDC_IMPLEMENTATION_GUIDE.md ¦ Generated for progress tracking
Sheet | Scope | Item Count
01 Architecture-Foundation | Tech stack, multi-tenancy, roles/routes, module pattern, folder structure, API conventions, collections checklist | 84
02 Employee-Org Setup | Slim employee master field mapping + Department/Designation/Grade/Region/District masters | 37
03 Loan Management | Loan Type & Eligibility setup, approval workflow, Application/Disbursement/EMI/Recovery/Closure transactions | 27
04 Leave Management | Leave Type/Holiday/Accrual setup, approval workflow, Balance/Application/Sandwich rule transactions | 22
05 Service Record | Promotion, Salary Revision, Transfer, Disciplinary, Document Repository transactions | 9
06 Workflow-Notification-Audit | Shared Workflow Master, Notification Master, User & Role Master, Audit Log | 12
07 Reports-Dashboards | Loan reports, Leave reports, MIS dashboard widgets | 14
08 Phases-Acceptance | 9-week phase plan (exit criteria) + 10-point UAT acceptance checklist | 26
TOTAL TRACKED ITEMS |  | 231
How to use this tracker
• Each sheet lists granular tasks under Section (Setup/Workflow/Transactions) and Sub-Section headers.
• Update Status (Not Started/In Progress/Blocked/In Review/Done) and Assigned Dev via dropdowns as work progresses.
• Layer column indicates DB / Backend / Frontend / combinations - useful for filtering dev-specific views.
• Priority and Sprint/Phase align with the guide's 4-phase, 9-week implementation plan.
• Use AutoFilter (enabled on every sheet) to filter by Status, Layer, Priority, or Sprint/Phase.

## 01 Architecture-Foundation
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
1. TECHNOLOGY STACK
Stack | Frontend - Super Admin | React 18 + Vite setup (frontend-admin) | Frontend | All UI components use .jsx; utilities/api clients use .js. Tenant provisioning only. | Not Started |  | High | Phase 1
Stack | Frontend - Client Admin | React 18 + Vite setup (frontend-client) | Frontend | HR, Finance, Manager, Org Admin portal. .jsx components. | Not Started |  | High | Phase 1
Stack | Frontend - Employee ESS | React 18 + Vite setup (frontend-employee) | Frontend | Self-service only portal. .jsx components. | Not Started |  | High | Phase 1
Stack | Backend | Node.js + Express API setup | Backend | REST API, all files .js (utilities, controllers, models, routes, middleware). | Not Started |  | Critical | Phase 1
Stack | Database | MongoDB + Mongoose setup | DB | All tenant data scoped by companyId. | Not Started |  | Critical | Phase 1
Stack | Auth | JWT (Bearer token) setup | Backend | Role array in token payload. | Not Started |  | Critical | Phase 1
Stack | Charts | Chart.js integration | Frontend | Dashboard widgets. | Not Started |  | Low | Phase 4
Stack | File Upload | Multer -> local/S3 config | Backend | PDF only for loan/leave attachments, max 5MB. | Not Started |  | Medium | Phase 1
2. ARCHITECTURE & MULTI-TENANCY
Multi-Tenancy | Tenant Model | Company (tenant) model | DB | Each MPBCDC deployment is one Company. All business collections carry companyId. | Not Started |  | Critical | Phase 1
Multi-Tenancy | Backend | tenantResolver.js - JWT companyId extraction | Backend | backend/middleware/tenantResolver.js: JWT companyId -> req.companyId; reject if missing. | Not Started |  | Critical | Phase 1
Multi-Tenancy | Backend | Data isolation on all queries | Backend | Every Mongoose query filters {companyId: req.companyId} across all controllers. | Not Started |  | Critical | Phase 1
Multi-Tenancy | Backend | Cross-tenant block | Backend | Strip companyId from request body in tenantResolver.js. | Not Started |  | Critical | Phase 1
Multi-Tenancy | Backend | Super Admin override | Backend | SUPER_ADMIN may pass x-company-id header to act on a tenant. | Not Started |  | Medium | Phase 1
Multi-Tenancy | Backend | Compound indexes | DB | Compound indexes on {companyId, ...} on all collections. | Not Started |  | High | Phase 1
Multi-Tenancy | Backend | Tenant isolation test | Backend | Expected result: Employee of Company A cannot read/write Company B data even with valid token from Company A. | Not Started |  | Critical | Phase 1 | Acceptance criteria #9
Multi-Tenancy | Frontend | PrivateRoutes.jsx per app | Frontend | Checks token and allowed roles before rendering <Outlet />, in each of the 3 apps. | Not Started |  | Critical | Phase 1
Multi-Tenancy | Frontend | Role -> module sidebar/menu map | Frontend | Sidebar/menu built from role->module map; do not rely on hiding links alone. | Not Started |  | High | Phase 1
Multi-Tenancy | Frontend | SubModuleGuard on sensitive routes | Frontend | Redirect to dashboard if role lacks permission. | Not Started |  | High | Phase 1
Multi-Tenancy | Frontend | Axios interceptor | Frontend | Attaches Authorization: Bearer <token>; never sends companyId in body. | Not Started |  | High | Phase 1
Multi-Tenancy | Frontend | LocalStorage namespace - Super Admin | Frontend | hrms_super_admin / token key auth_token; company context optional via header. | Not Started |  | Medium | Phase 1
Multi-Tenancy | Frontend | LocalStorage namespace - Client Admin | Frontend | hrms_client_admin / token key hrms_client_admin:token; company context from JWT companyId. | Not Started |  | Medium | Phase 1
Multi-Tenancy | Frontend | LocalStorage namespace - Employee ESS | Frontend | hrms_employee / token key hrms_employee:token; company context from JWT companyId. | Not Started |  | Medium | Phase 1
Multi-Tenancy | Frontend | Cross-portal access block test | Frontend | Expected result: CLIENT_ADMIN opening Employee portal URL redirected to login with access-denied message; Employee cannot navigate to /settings/* even via URL. | Not Started |  | Critical | Phase 1 | Acceptance criteria #1
3. ROLES, PORTALS & ROUTE SEGREGATION
Roles & Routing | Role Matrix | Define 7 roles | Backend | SUPER_ADMIN, CLIENT_ADMIN, HR_OFFICER, FINANCE_OFFICER, REPORTING_MANAGER, REGIONAL_MANAGER, EMPLOYEE. | Not Started |  | Critical | Phase 1 | MPBCDC 'Administrator' maps to CLIENT_ADMIN
Roles & Routing | Super Admin Portal | /login, /dashboard, /companies, /companies/:id, /companies/:id/users, /audit-logs | Frontend | Login URL e.g. https://admin.mpbcdc.example.com/login | Not Started |  | High | Phase 1
Roles & Routing | Client Admin Portal | /settings/organization/* | Frontend | Dept, Designation, Grade, Region, District - CLIENT_ADMIN. | Not Started |  | High | Phase 1
Roles & Routing | Client Admin Portal | /settings/employees/* | Frontend | Employee master CRUD - CLIENT_ADMIN, HR_OFFICER. | Not Started |  | High | Phase 1
Roles & Routing | Client Admin Portal | /settings/loan/* | Frontend | Loan type, eligibility, workflow - CLIENT_ADMIN. | Not Started |  | High | Phase 3
Roles & Routing | Client Admin Portal | /settings/leave/* | Frontend | Leave type, accrual, holiday, workflow - CLIENT_ADMIN. | Not Started |  | High | Phase 2
Roles & Routing | Client Admin Portal | /settings/workflow/* | Frontend | Approval matrix - CLIENT_ADMIN. | Not Started |  | High | Phase 1
Roles & Routing | Client Admin Portal | /settings/notifications/* | Frontend | Notification templates - CLIENT_ADMIN. | Not Started |  | Medium | Phase 4
Roles & Routing | Client Admin Portal | /settings/users/* | Frontend | User & role assignment - CLIENT_ADMIN. | Not Started |  | High | Phase 1
Roles & Routing | Client Admin Portal | /transactions/loans/* | Frontend | Loan applications, approvals, disbursement - HR, Finance, Manager. | Not Started |  | Critical | Phase 3
Roles & Routing | Client Admin Portal | /transactions/leaves/* | Frontend | Leave applications, approvals - HR, Manager. | Not Started |  | Critical | Phase 2
Roles & Routing | Client Admin Portal | /service-records/* | Frontend | Employee service book - HR, Manager, CLIENT_ADMIN. | Not Started |  | Medium | Phase 4
Roles & Routing | Client Admin Portal | /reports/* | Frontend | All reports, role-filtered. | Not Started |  | Medium | Phase 4 | Login URL e.g. https://portal.mpbcdc.example.com/login
Roles & Routing | Employee ESS Portal | /login, /dashboard | Frontend | Employee Code + Password login; personal dashboard. | Not Started |  | Critical | Phase 1 | Login URL e.g. https://ess.mpbcdc.example.com/login
Roles & Routing | Employee ESS Portal | /loans/apply, /loans/applied, /loans/:id/schedule | Frontend | New loan application, my loan list & status, EMI schedule. | Not Started |  | Critical | Phase 3
Roles & Routing | Employee ESS Portal | /leaves/apply, /leaves/history, /leaves/balance | Frontend | New leave application, leave history, leave balance. | Not Started |  | Critical | Phase 2
Roles & Routing | Employee ESS Portal | /profile, /documents, /notifications | Frontend | Limited personal view, own documents only, in-app notifications. | Not Started |  | Medium | Phase 1
Roles & Routing | Backend Authorization | auth + tenantResolver + authorize() middleware chain | Backend | Mirror authMiddleware.js, tenantResolver.js, authorizeRoles.js on every route. | Not Started |  | Critical | Phase 1
Roles & Routing | Backend Authorization | Self-scope enforcement test | Backend | Expected result: POST /api/loans with EMPLOYEE token creates application for self only; cannot create for another employeeId. | Not Started |  | Critical | Phase 1 | Acceptance criteria driven
4. MODULE PATTERN: SETUP VS TRANSACTIONS
Module Pattern | Convention | Setup vs Transactions folder/route convention | Backend+Frontend | SETUP -> /settings/<module>/* (master CRUD, rules, workflow). TRANSACTIONS -> /transactions/<module>/* (apply, approver queues, post-approval processing). | Not Started |  | High | Phase 1
FOLDER STRUCTURE
Folder Structure | Backend | backend/models/, controllers/, routes/, services/, middleware/ | Backend | models/: MpbcdcEmployee.js, Department.js, LoanType.js, LoanApplication.js, LoanEmiSchedule.js, LeaveType.js, LeaveApplication.js, etc. services/: loanEligibilityService.js, loanScheduleService.js, leaveCalculationService.js, leaveAccrualService.js. middleware/: authMiddleware.js, tenantResolver.js, authorizeRoles.js. | Not Started |  | High | Phase 1
Folder Structure | Frontend Admin | frontend-admin/src/ (SUPER_ADMIN, .jsx pages) | Frontend |  | Not Started |  | Medium | Phase 1
Folder Structure | Frontend Client | frontend-client/src/pages/settings/{organization,employees,loan,leave}/, transactions/{loans,leaves}/, routes/PrivateRoutes.jsx | Frontend |  | Not Started |  | High | Phase 1
Folder Structure | Frontend Employee | frontend-employee/src/pages/{loans,leaves}/, routes/PrivateRoutes.jsx | Frontend |  | Not Started |  | High | Phase 1
API CONVENTIONS
API Conventions | Base path | /api | Backend |  | Not Started |  | Medium | Phase 1
API Conventions | Response shape | {success:true,data:...} / {success:false,error:'...'} | Backend | Standard response envelope. | Not Started |  | High | Phase 1
API Conventions | Pagination | ?page=1&limit=20 | Backend |  | Not Started |  | Medium | Phase 1
API Conventions | Auto numbers | LN-2026-00001, LV-2026-00001, SR-2026-00001 | Backend | Per company sequence. | Not Started |  | High | Phase 1
API Conventions | File upload | multipart/form-data, max 5MB, PDF only | Backend |  | Not Started |  | Medium | Phase 1
API Conventions | Dates | ISO 8601 in API; DD-MMM-YYYY in UI | Backend+Frontend |  | Not Started |  | Medium | Phase 1
MONGODB COLLECTIONS CHECKLIST
Collections | MongoDB | companies | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | users | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | mpbcdc_employees | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | departments | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | designations | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | grades | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | regions | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | districts | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | loan_types | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | loan_eligibility_rules | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | loan_applications | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | loan_approvals | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | loan_disbursements | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | loan_emi_schedules | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | loan_recoveries | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | loan_closures | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | leave_types | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | holidays | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | leave_accrual_rules | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | leave_balances | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | leave_applications | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | leave_approvals | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | promotion_histories | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | salary_revisions | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | transfer_histories | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | disciplinary_cases | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | employee_documents | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | approval_matrices | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | notification_templates | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | notifications | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1
Collections | MongoDB | audit_logs | DB | Collection to be created per schema. | Not Started |  | Medium | Phase 1

## 02 Employee-Org Setup
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
MASTER DATA SETUP - EMPLOYEE FIELD MAPPING
Employee Master | Field Mapping | Employee ID | DB | _id (ObjectId, auto, hidden) | Not Started |  | High | Phase 1 | MongoDB primary key
Employee Master | Field Mapping | Employee Code | DB | employeeCode String(20), Mandatory, Text | Not Started |  | High | Phase 1 | Unique per companyId
Employee Master | Field Mapping | Employee Name | DB | employeeName String(200), Mandatory, Text | Not Started |  | High | Phase 1 | Single field, not first/last split
Employee Master | Field Mapping | Gender | DB | gender String(20), Mandatory, Dropdown | Not Started |  | High | Phase 1 | Male / Female / Other
Employee Master | Field Mapping | Date of Birth | DB | dateOfBirth Date, Mandatory, Date picker | Not Started |  | High | Phase 1
Employee Master | Field Mapping | Joining Date | DB | joiningDate Date, Mandatory, Date picker | Not Started |  | High | Phase 1 | Used for service period & leave pro-rata
Employee Master | Field Mapping | Retirement Date | DB | retirementDate Date, Mandatory, Date picker | Not Started |  | High | Phase 1 | Used for loan retirement buffer rule
Employee Master | Field Mapping | Mobile Number | DB | mobileNumber String(15), Mandatory, Text | Not Started |  | High | Phase 1 | 10-digit validation
Employee Master | Field Mapping | Email ID | DB | email String(100), Mandatory, Email | Not Started |  | High | Phase 1 | Login optional secondary
Employee Master | Field Mapping | Aadhaar Number | DB | aadhaarNumber String(12), Mandatory, Text | Not Started |  | High | Phase 1 | Mask display in UI
Employee Master | Field Mapping | PAN Number | DB | panNumber String(10), Mandatory, Text | Not Started |  | High | Phase 1 | Uppercase
Employee Master | Field Mapping | Department | DB | departmentId ObjectId, Mandatory, Lookup | Not Started |  | High | Phase 1 | -> Department
Employee Master | Field Mapping | Designation | DB | designationId ObjectId, Mandatory, Lookup | Not Started |  | High | Phase 1 | -> Designation
Employee Master | Field Mapping | Grade | DB | gradeId ObjectId, Mandatory, Lookup | Not Started |  | High | Phase 1 | -> Grade
Employee Master | Field Mapping | Region | DB | regionId ObjectId, Mandatory, Lookup | Not Started |  | High | Phase 1 | -> Region
Employee Master | Field Mapping | District | DB | districtId ObjectId, Mandatory, Lookup | Not Started |  | High | Phase 1 | -> District
Employee Master | Field Mapping | Reporting Manager | DB | reportingManagerId ObjectId, Mandatory, Employee lookup | Not Started |  | High | Phase 1 | Same company, cannot be self
Employee Master | Field Mapping | Employment Type | DB | employmentType String(50), Mandatory, Dropdown | Not Started |  | High | Phase 1 | Permanent / Contract / etc.
Employee Master | Field Mapping | Status | DB | status String(20), Mandatory, Toggle | Not Started |  | High | Phase 1 | Active / Inactive
Employee Master | Field Mapping | Company ID | DB | companyId ObjectId, Mandatory, Hidden | Not Started |  | High | Phase 1 | Tenant scope
Employee Master | Field Mapping | Gross Salary | DB | grossSalary Number, Mandatory*, Number | Not Started |  | High | Phase 1 | *Required for loan eligibility; HR maintains via salary revision txn
EMPLOYEE MASTER - BY LAYER
Employee Master | DB | mpbcdc_employees collection | DB | Index {companyId, employeeCode} unique. Expected result: no duplicate codes within tenant. | Not Started |  | Critical | Phase 1
Employee Master | Backend | POST/GET/PUT /api/employees | Backend | Validate lookups belong to same companyId; block delete if open loans/leaves. | Not Started |  | Critical | Phase 1
Employee Master | Backend | Inactive employee login block | Backend | Expected result: Inactive employee cannot log in. | Not Started |  | Critical | Phase 1 | Acceptance criteria #10
Employee Master | Frontend (Setup) | EmployeeList.jsx, EmployeeForm.jsx | Frontend | frontend-client/src/pages/settings/employees/. HR/Admin sees paginated list, create/edit with lookup dropdowns. | Not Started |  | High | Phase 1
Employee Master | Frontend (ESS) | Profile.jsx - read-only subset | Frontend | frontend-employee/src/pages/Profile.jsx. Employee sees name, dept, designation, grade, manager, joining date only. | Not Started |  | Medium | Phase 1
ORGANIZATION SETUP MASTERS
Org Setup | Department Master - DB | Department fields: _id, name, headEmployeeId, effectiveDate, status | DB | models/Department.js. companyId scoped. | Not Started |  | High | Phase 1
Org Setup | Department Master - Backend | GET/POST/PUT /api/departments | Backend | routes/departmentRoutes.js, controllers/departmentController.js | Not Started |  | High | Phase 1
Org Setup | Department Master - Frontend | DepartmentMaster.jsx | Frontend | pages/settings/organization/DepartmentMaster.jsx | Not Started |  | High | Phase 1
Org Setup | Designation Master | code, name, gradeId, payScale, status | DB | Designation ID, Name, Grade (lookup), Pay Scale, Status. | Not Started |  | High | Phase 1
Org Setup | Designation Master | CRUD API + Frontend page | Backend+Frontend | Follow same pattern as Department Master. | Not Started |  | High | Phase 1
Org Setup | Grade Master | code, name, approvalMatrixApplicable, status | DB | Grade Code, Grade Name, Approval Matrix Applicable (Boolean), Status. | Not Started |  | High | Phase 1
Org Setup | Grade Master | CRUD API + Frontend page | Backend+Frontend | Follow same pattern as Department Master. | Not Started |  | High | Phase 1
Org Setup | Region Master | code, name, managerEmployeeId | DB | Region Code, Region Name, Regional Manager. | Not Started |  | High | Phase 1
Org Setup | Region Master | CRUD API + Frontend page | Backend+Frontend | Follow same pattern as Department Master. | Not Started |  | High | Phase 1
Org Setup | District Master | code, name, regionId | DB | District Code, District Name, Region Mapping. | Not Started |  | High | Phase 1
Org Setup | District Master | CRUD API + Frontend page | Backend+Frontend | Cascading dropdown - Expected result: District list filters by selected Region in Employee form. | Not Started |  | High | Phase 1

## 03 Loan Management
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
MASTER DATA SETUP
Master Data Setup | Loan Type Master - DB | models/LoanType.js | DB | {companyId, code} unique. Fields: code, name, isEducationLoan, isComputerLoan, isVehicleLoan, isHomeLoan, isMarriageLoan, maxAmount, maxTenureMonths, interestRate, minServiceYears, salaryMultiplier, isActive. | Not Started |  | Critical | Phase 3
Master Data Setup | Loan Type Master - Backend | CRUD /api/loan-types | Backend | routes/loanTypeRoutes.js - roles: CLIENT_ADMIN. | Not Started |  | Critical | Phase 3
Master Data Setup | Loan Type Master - Frontend | LoanTypeList.jsx, LoanTypeForm.jsx | Frontend | pages/settings/loan/. Expected result: Admin creates 'Education Loan' with max 5,00,000, 60 months, 8% interest; employee apply screen shows only active types. | Not Started |  | Critical | Phase 3
Master Data Setup | Loan Eligibility Config - DB | models/LoanEligibilityRule.js | DB | Fields: ruleCode (default DEFAULT), minServiceMonths, salaryMultiplier, maxEmiPercentOfGross (default 60), retirementBufferMonths (default 3), effectiveDate, status. | Not Started |  | Critical | Phase 3
Master Data Setup | Loan Eligibility Config - Backend | loanEligibilityService.js | Backend | services/loanEligibilityService.js - pure function calculateEligibility(employee, loanType, requestedAmount, requestedTenure). Rules: EMI <=60% gross after existing EMI; retain >=40% gross; loan closes >=3 months before retirementDate; sum existing active loan EMIs. | Not Started |  | Critical | Phase 3
Master Data Setup | Loan Eligibility Config - Frontend | LoanEligibilityConfig.jsx | Frontend | pages/settings/loan/. Expected result: apply form calls GET /api/loans/preview-eligibility and shows derived fields before submit. | Not Started |  | Critical | Phase 3
APPROVAL WORKFLOW
Approval Workflow | Workflow States | Draft -> Submitted -> Manager -> HR -> Finance -> Disbursed -> Closed (Rejected terminal) | Backend | State machine for loan application lifecycle. | Not Started |  | Critical | Phase 3
Approval Workflow | Approval Matrix (Setup) | Level 1: REPORTING_MANAGER (3d), Level 2: HR_OFFICER (3d), Level 3: FINANCE_OFFICER (5d) | Backend | Uses shared Workflow Master (ApprovalMatrix.js), module=LOAN. | Not Started |  | Critical | Phase 3
Approval Workflow | DB | models/LoanApproval.js | DB | One row per approval action: applicationId, approverRole, approverUserId, approvedAt, decision, remarks, signatureFilePath/signatureDataUrl, nextApproverRole. | Not Started |  | Critical | Phase 3
Approval Workflow | Backend | loanWorkflowService.js | Backend | getNextApprover(), canApprove(user, application). | Not Started |  | Critical | Phase 3
Approval Workflow | Frontend (Setup) | LoanApprovalWorkflow.jsx | Frontend | pages/settings/loan/LoanApprovalWorkflow.jsx | Not Started |  | High | Phase 3
Approval Workflow | Frontend (Txn) | LoanApprovalQueue.jsx | Frontend | pages/transactions/loans/LoanApprovalQueue.jsx. Expected result: HR approval button disabled until Manager approves; Finance queue shows only HR-approved apps; rejection at any level sets status Rejected and notifies employee. | Not Started |  | Critical | Phase 3 | Acceptance criteria #5
TRANSACTIONS
Transactions | Loan Application - DB | models/LoanApplication.js | DB | Header: applicationNo (LN-YYYY-#####), applicationDate, employeeId, loanTypeId, requestedAmount, requestedTenureMonths, purpose, coveringNote, attachmentPath. System-derived: grossSalaryAtApplication, existingEmiTotal, maxEligibleAmount, maxEligibleEmi, remainingServiceYears, eligibilityStatus, ineligibilityReasons[]. | Not Started |  | Critical | Phase 3
Transactions | Loan Application - Backend | POST /api/loan-applications, PUT /:id/submit | Backend | EMPLOYEE role; block submit if eligibilityStatus !== 'Eligible'. | Not Started |  | Critical | Phase 3
Transactions | Loan Application - Frontend (ESS) | ApplyLoan.jsx wizard | Frontend | pages/loans/ApplyLoan.jsx - select type -> amount/tenure -> eligibility panel -> upload -> submit. Expected result: employee with 1yr service applying Home Loan (min 5yr) sees 'Ineligible: Service period insufficient', Submit disabled. | Not Started |  | Critical | Phase 3 | Acceptance criteria #4
Transactions | Loan Application - Frontend (Admin) | LoanApplicationList.jsx | Frontend | pages/transactions/loans/LoanApplicationList.jsx - filters by status, role-based queues. | Not Started |  | High | Phase 3
Transactions | Loan Disbursement - DB | models/LoanDisbursement.js | DB | Fields: disbursementNo, loanNo (assigned at disbursement), sanctionAmount, interestRate, emiAmount, disbursementDate, bankAccount, financeRemarks, voucherNo. | Not Started |  | Critical | Phase 3
Transactions | Loan Disbursement - Backend | POST /api/loan-applications/:id/disburse | Backend | FINANCE_OFFICER only; triggers EMI schedule generation. Business rule: disbursement after 20th of month -> first EMI due next month. | Not Started |  | Critical | Phase 3 | Acceptance criteria #6
Transactions | Loan Disbursement - Frontend | LoanDisbursementForm.jsx | Frontend | pages/transactions/loans/. Expected result: status=Disbursed, employee notified, EMI schedule visible in ESS. | Not Started |  | Critical | Phase 3
Transactions | EMI Schedule - DB | models/LoanEmiSchedule.js | DB | Fields: _id, loanNo, emiNo, dueDate, principalComponent, interestComponent, emiAmount, outstandingBalance, deductionStatus (Pending/Deducted/Skipped). | Not Started |  | Critical | Phase 3
Transactions | EMI Schedule - Backend | loanScheduleService.js | Backend | generateSchedule(loanNo, sanctionAmount, rate, tenure, startDate) - reducing balance method. | Not Started |  | Critical | Phase 3
Transactions | EMI Schedule - Frontend (ESS) | RepaymentSchedule.jsx | Frontend | pages/loans/RepaymentSchedule.jsx - table + progress bar. | Not Started |  | High | Phase 3
Transactions | EMI Schedule - Frontend (Admin) | EmiScheduleView.jsx | Frontend | pages/transactions/loans/EmiScheduleView.jsx | Not Started |  | High | Phase 3
Transactions | Loan Recovery - DB | models/LoanRecovery.js | DB | Fields: _id, loanNo, payrollMonth (YYYY-MM), emiAmount, recoveryDate, status, balanceOutstanding. | Not Started |  | High | Phase 3
Transactions | Loan Recovery - Backend | POST /api/loan-recoveries | Backend | Mark EMI deducted for payroll month; update schedule row. | Not Started |  | High | Phase 3
Transactions | Loan Recovery - Frontend | LoanRecoveryRegister.jsx | Frontend | pages/transactions/loans/LoanRecoveryRegister.jsx | Not Started |  | High | Phase 3
Transactions | Loan Closure | closureNo, loanNo, closureDate, outstandingAmount, closureType, certificateNo | DB | closureType: Regular / Prepayment / Settlement. Expected result: closed loan no longer in active EMI deduction; employee can download closure certificate PDF. | Not Started |  | High | Phase 3

## 04 Leave Management
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
MASTER DATA SETUP
Master Data Setup | Leave Type Master - DB | models/LeaveType.js | DB | Fields: code (CL/SL/EL/SPL), name, annualEntitlement, halfDayAllowed, encashmentAllowed, carryForwardAllowed, maxAccumulation (EL default 300), sandwichRuleApplicable, hrApprovalRequired. | Not Started |  | Critical | Phase 2
Master Data Setup | Leave Type Master - Backend | CRUD /api/leave-types | Backend | Supported types: CL (Casual), SL (Sick), EL (Earned), Special Leave. | Not Started |  | Critical | Phase 2
Master Data Setup | Leave Type Master - Frontend | LeaveTypeMaster.jsx | Frontend | pages/settings/leave/LeaveTypeMaster.jsx | Not Started |  | Critical | Phase 2
Master Data Setup | Holiday Master - DB | models/Holiday.js | DB | Fields: _id, name, type (National/Regional/Optional), date, state, regionId. | Not Started |  | High | Phase 2
Master Data Setup | Holiday Master - Backend | /api/holidays CRUD | Backend |  | Not Started |  | High | Phase 2
Master Data Setup | Holiday Master - Frontend | HolidayCalendar.jsx | Frontend | pages/settings/leave/HolidayCalendar.jsx | Not Started |  | High | Phase 2
Master Data Setup | Leave Accrual Rule - DB | models/LeaveAccrualRule.js | DB | Fields: ruleCode, leaveTypeId (EL), frequency (Half-Yearly), creditDays (15), proRataApplicable (true), accumulationLimit (300), effectiveDate. | Not Started |  | Critical | Phase 2
Master Data Setup | Leave Accrual Rule - Backend | leaveAccrualService.js | Backend | Cron/job on Jan 1 & Jul 1; pro-rata for new joiners. Expected result: new joiner Apr 1 gets pro-rated EL credit; accrual job idempotent (running twice does not double-credit). | Not Started |  | Critical | Phase 2
Master Data Setup | Leave Accrual Rule - Frontend | LeaveAccrualSetup.jsx | Frontend | pages/settings/leave/LeaveAccrualSetup.jsx | Not Started |  | High | Phase 2
APPROVAL WORKFLOW
Approval Workflow | Workflow Flow | Employee -> Reporting Manager -> HR (optional per type) -> Balance Update -> Notification | Backend | Uses shared Workflow Master. | Not Started |  | Critical | Phase 2
Approval Workflow | DB | models/LeaveApproval.js | DB | Fields: Application No, Approver, Approval Date, Decision, Remarks, Escalation Status. | Not Started |  | Critical | Phase 2
Approval Workflow | Backend | leaveWorkflowService.js | Backend | Expected result: Manager rejects -> balance not deducted. Manager approves + HR required -> waits for HR. All approved -> leaveBalanceService.deduct() runs atomically. | Not Started |  | Critical | Phase 2 | Acceptance criteria #7
Approval Workflow | Frontend (Setup) | LeaveApprovalWorkflow.jsx | Frontend | pages/settings/leave/LeaveApprovalWorkflow.jsx | Not Started |  | High | Phase 2
Approval Workflow | Frontend (Txn) | LeaveApprovalQueue.jsx | Frontend | pages/transactions/leaves/LeaveApprovalQueue.jsx | Not Started |  | Critical | Phase 2
TRANSACTIONS
Transactions | Leave Balance (Ledger) - DB | models/LeaveBalance.js | DB | Index {companyId, employeeId, leaveTypeId, period}. Fields: employeeId, leaveTypeId, openingBalance, accrued, availed, closingBalance, period (e.g. 2026 or 2026-H1). | Not Started |  | Critical | Phase 2
Transactions | Leave Balance (Ledger) - Backend | GET /api/leave-balances/my, GET /api/leave-balances | Backend | my for EMPLOYEE; full for HR. | Not Started |  | Critical | Phase 2
Transactions | Leave Balance (Ledger) - Frontend | LeaveBalance.jsx (ESS), LeaveBalanceReport.jsx (Admin) | Frontend | pages/leaves/LeaveBalance.jsx and pages/transactions/leaves/LeaveBalanceReport.jsx | Not Started |  | High | Phase 2
Transactions | Leave Application - DB | models/LeaveApplication.js | DB | Fields: applicationNo, employeeId, leaveTypeId, fromDate, toDate, totalDays (system calculated), isHalfDay, reason, attachmentPath, balanceBefore, balanceAfter, status (Draft/Submitted/Approved/Rejected). | Not Started |  | Critical | Phase 2
Transactions | Leave Application - Backend | leaveCalculationService.js | Backend | Working days, holidays, sandwich rule calculation. | Not Started |  | Critical | Phase 2
Transactions | Leave Application - Frontend | ApplyLeave.jsx | Frontend | pages/leaves/ApplyLeave.jsx. Expected result: employee with 2 CL balance applying for 3 days sees validation error before submit; approved leave reduces balance, rejected does not. | Not Started |  | Critical | Phase 2
Transactions | Sandwich Rule - Backend | leaveCalculationService.calculateDays(from, to, regionId, leaveType) | Backend | Logic: Fri leave + Sat-Sun holiday + Mon leave = 4 days deducted (not 2), when sandwichRuleApplicable is enabled on leave type. | Not Started |  | High | Phase 2 | Acceptance criteria #3
Transactions | Sandwich Rule - Frontend | Breakdown display | Frontend | Show breakdown: Working days / Holidays sandwiched / Total deducted. | Not Started |  | High | Phase 2

## 05 Service Record
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
STRUCTURE & ACCESS
Access Control | Visibility | Visible to HR, CLIENT_ADMIN, REPORTING_MANAGER (direct reports only) | Backend | Not visible to EMPLOYEE except limited profile. Expected result: Manager opens service record for reportee, sees promotion/transfer history; cannot open unrelated employee. | Not Started |  | Critical | Phase 4
Structure | Service Record Header | Header fields: Service Record Number (auto SR-YYYY-#####), employeeId, Employee Name, DOJ, Current Designation/Grade/Department/Region (live from Employee) | DB | Read-only snapshot. | Not Started |  | High | Phase 4
TRANSACTIONS
Transactions | Promotion History | PromotionHistory.js / POST /api/service-records/:employeeId/promotions | DB+Backend | Backend route: POST /api/service-records/:employeeId/promotions. Frontend: ServiceRecord/PromotionForm.jsx. | Not Started |  | Medium | Phase 4
Transactions | Salary Revision | SalaryRevision.js / POST .../salary-revisions | DB+Backend | Backend route: POST .../salary-revisions. Frontend: ServiceRecord/SalaryRevisionForm.jsx - updates employee.grossSalary. | Not Started |  | Medium | Phase 4
Transactions | Transfer History | TransferHistory.js / POST .../transfers | DB+Backend | Backend route: POST .../transfers. Frontend: ServiceRecord/TransferForm.jsx - updates region/dept on employee. | Not Started |  | Medium | Phase 4
Transactions | Disciplinary Action | DisciplinaryCase.js / POST .../disciplinary | DB+Backend | Backend route: POST .../disciplinary. Frontend: ServiceRecord/DisciplinaryForm.jsx. | Not Started |  | Medium | Phase 4
Transactions | Document Repository | EmployeeDocument.js / POST .../documents (multipart) | DB+Backend | Backend route: POST .../documents (multipart). Frontend: ServiceRecord/DocumentUpload.jsx. | Not Started |  | Medium | Phase 4
Transactions | Document Categories | Appointment Letter, Promotion Order, Transfer Order, Educational Certificates, Identity Documents, Disciplinary Documents, Retirement Documents | DB | Document category enum for EmployeeDocument.js. | Not Started |  | Medium | Phase 4
Transactions | Salary Revision Integration | Loan eligibility recalculation link | Backend | Expected result: salary revision reflects in next loan eligibility calculation. | Not Started |  | High | Phase 4 | Acceptance criteria #8

## 06 Workflow-Notification-Audit
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
WORKFLOW MASTER (SHARED SETUP)
Workflow Master | DB | models/ApprovalMatrix.js | DB | Fields: code, module (LOAN/LEAVE), gradeId, level (1,2,3...), approverRole, escalationDays, isActive. | Not Started |  | Critical | Phase 1
Workflow Master | Backend | /api/workflow-matrix | Backend |  | Not Started |  | Critical | Phase 1
Workflow Master | Frontend | ApprovalMatrix.jsx | Frontend | pages/settings/workflow/ApprovalMatrix.jsx | Not Started |  | High | Phase 1
NOTIFICATION MASTER
Notification Master | DB | models/NotificationTemplate.js, models/Notification.js | DB | Fields: templateCode, eventName, emailBody, smsBody, whatsappBody, triggerStage. In-app inbox via Notification.js. | Not Started |  | Medium | Phase 4
Notification Master | Backend | notificationService.js | Backend | Called from workflow hooks. Events: Loan Submitted, Loan Approved, Loan Rejected, Leave Approved, Leave Rejected, Promotion Updated, EMI Reminder, Retirement Reminder. | Not Started |  | Medium | Phase 4
Notification Master | Frontend | NotificationTemplates.jsx + bell icon inbox | Frontend | pages/settings/notifications/NotificationTemplates.jsx; bell icon inbox across all portals. | Not Started |  | Medium | Phase 4
USER & ROLE MASTER
User & Role Master | DB | models/User.js | DB | Fields: _id, loginId (Employee Code), passwordHash, employeeId, roles[], companyId, lastLoginAt. | Not Started |  | Critical | Phase 1
User & Role Master | Backend | /api/auth/login, /api/users | Backend |  | Not Started |  | Critical | Phase 1
User & Role Master | Frontend | UserManagement.jsx | Frontend | pages/settings/users/UserManagement.jsx | Not Started |  | High | Phase 1
AUDIT
Audit | DB | models/AuditLog.js | DB | Fields: {companyId, userId, action, entity, entityId, before, after, timestamp}. | Not Started |  | Medium | Phase 4
Audit | Backend | Mongoose plugin / middleware on write ops | Backend | Auto-capture on write operations. | Not Started |  | Medium | Phase 4
Audit | Frontend | AuditLogList.jsx | Frontend | pages/settings/audit/AuditLogList.jsx - CLIENT_ADMIN only. | Not Started |  | Low | Phase 4

## 07 Reports-Dashboards
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
LOAN REPORTS
Loan Reports | Loan Eligibility Report | /api/reports/loans/eligibility | Backend | Roles: HR, Admin | Not Started |  | Medium | Phase 4
Loan Reports | Loan Application Register | /api/reports/loans/applications | Backend | Roles: HR, Finance, Admin | Not Started |  | Medium | Phase 4
Loan Reports | Loan Sanction Register | /api/reports/loans/sanctions | Backend | Roles: Finance, Admin | Not Started |  | Medium | Phase 4
Loan Reports | Disbursement Report | /api/reports/loans/disbursements | Backend | Roles: Finance | Not Started |  | Medium | Phase 4
Loan Reports | EMI Recovery Register | /api/reports/loans/recoveries | Backend | Roles: Finance | Not Started |  | Medium | Phase 4
Loan Reports | Outstanding Loan Report | /api/reports/loans/outstanding | Backend | Roles: Finance, HR | Not Started |  | Medium | Phase 4
Loan Reports | Loan Closure Report | /api/reports/loans/closures | Backend | Roles: Finance | Not Started |  | Medium | Phase 4
LEAVE REPORTS
Leave Reports | Employee Leave Balance | /api/reports/leaves/balances | Backend |  | Not Started |  | Medium | Phase 4
Leave Reports | Leave Register | /api/reports/leaves/register | Backend |  | Not Started |  | Medium | Phase 4
Leave Reports | Pending Approvals | /api/reports/leaves/pending | Backend |  | Not Started |  | Medium | Phase 4
Leave Reports | Leave Utilization | /api/reports/leaves/utilization | Backend |  | Not Started |  | Medium | Phase 4
Leave Reports | Half Day Leave | /api/reports/leaves/half-day | Backend |  | Not Started |  | Medium | Phase 4
MIS DASHBOARD CARDS
Dashboards | Client Admin Widgets | Total/Active Employees, Pending Loans, Pending Leaves, Outstanding Loans, Retirement Due | Frontend | Dashboard cards for Client Admin portal. | Not Started |  | Medium | Phase 4
Dashboards | Employee Widgets | Leave balances, Active loan EMI, Next EMI date, Pending requests | Frontend | Dashboard cards for Employee ESS portal. | Not Started |  | Medium | Phase 4

## 08 Phases-Acceptance
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
PHASE 1 - FOUNDATION (WEEK 1-2)
Phase 1 | Foundation | Company + User + Auth + tenant middleware | Backend+DB | Core multi-tenant auth foundation. | Not Started |  | Critical | Phase 1
Phase 1 | Foundation | Three frontends with PrivateRoutes role gates | Frontend | frontend-admin, frontend-client, frontend-employee. | Not Started |  | Critical | Phase 1
Phase 1 | Foundation | Organization masters + slim Employee master | Backend+DB | Dept/Designation/Grade/Region/District + MpbcdcEmployee model. | Not Started |  | Critical | Phase 1
Phase 1 | Done When | Super Admin creates company; Client Admin logs in and creates employee; Employee logs in to ESS | All | Exit criteria for Phase 1. | Not Started |  | Critical | Phase 1
PHASE 2 - LEAVE MODULE (WEEK 3-4)
Phase 2 | Leave Module | Leave setup (types, holidays, accrual, workflow) | All |  | Not Started |  | Critical | Phase 2
Phase 2 | Leave Module | Leave application + approval + balance ledger | All |  | Not Started |  | Critical | Phase 2
Phase 2 | Leave Module | Sandwich rule + half-day | Backend |  | Not Started |  | High | Phase 2
Phase 2 | Done When | End-to-end leave apply -> manager approve -> balance reduced | All | Exit criteria for Phase 2. | Not Started |  | Critical | Phase 2
PHASE 3 - LOAN MODULE (WEEK 5-7)
Phase 3 | Loan Module | Loan setup (types, eligibility) | All |  | Not Started |  | Critical | Phase 3
Phase 3 | Loan Module | Application + multi-level approval | All |  | Not Started |  | Critical | Phase 3
Phase 3 | Loan Module | Disbursement + EMI schedule + recovery + closure | All |  | Not Started |  | Critical | Phase 3
Phase 3 | Done When | End-to-end loan with eligibility block, 3-level approval, EMI schedule visible in ESS | All | Exit criteria for Phase 3. | Not Started |  | Critical | Phase 3
PHASE 4 - SERVICE RECORD + REPORTS (WEEK 8-9)
Phase 4 | Service Record | Service book transactions + documents | All |  | Not Started |  | Medium | Phase 4
Phase 4 | Reports | Reports + dashboards | All |  | Not Started |  | Medium | Phase 4
Phase 4 | Notifications | Notifications + audit | All |  | Not Started |  | Medium | Phase 4
Phase 4 | Done When | HR maintains service book; all client-listed reports exportable | All | Exit criteria for Phase 4. | Not Started |  | Medium | Phase 4
ACCEPTANCE CRITERIA SUMMARY (10-POINT CHECKLIST)
Acceptance Criteria | #1 | Employee opens frontend-client URL | All | Expected result: Redirected to login; access denied | Not Started |  | Critical | Phase 4 (UAT)
Acceptance Criteria | #2 | Client Admin creates employee | All | Expected result: Employee code unique per company; lookups validated | Not Started |  | Critical | Phase 4 (UAT)
Acceptance Criteria | #3 | Employee applies leave spanning sandwich weekend | All | Expected result: Days deducted per sandwich rule when enabled | Not Started |  | Critical | Phase 4 (UAT)
Acceptance Criteria | #4 | Employee applies loan exceeding EMI limit | All | Expected result: Submit blocked; reasons displayed | Not Started |  | Critical | Phase 4 (UAT)
Acceptance Criteria | #5 | Manager approves loan | All | Expected result: HR queue shows application; Finance queue empty | Not Started |  | Critical | Phase 4 (UAT)
Acceptance Criteria | #6 | Finance disburses on 25th | All | Expected result: First EMI due next month | Not Started |  | Critical | Phase 4 (UAT)
Acceptance Criteria | #7 | Leave approved | All | Expected result: closingBalance reduced by totalDays | Not Started |  | Critical | Phase 4 (UAT)
Acceptance Criteria | #8 | HR uploads promotion order | All | Expected result: Visible in service record; not in employee ESS | Not Started |  | Critical | Phase 4 (UAT)
Acceptance Criteria | #9 | Two companies in same DB | All | Expected result: Zero data leakage across companyId | Not Started |  | Critical | Phase 4 (UAT)
Acceptance Criteria | #10 | Inactive employee login | All | Expected result: Authentication fails | Not Started |  | Critical | Phase 4 (UAT)